## User story
User Story ID | User Story Title | User Story | Notes
US 1 | Recent activity | User want to view the recent activities and have access to it.
US 2 |  | User want to edit the text that transcribed.
US 3 |  | User want to play back the recordings.
US 4 |  | User want to search files from recent activity on the basis of name or date.
US 5 |  | User want to see the listing in recent activity seperated by numbers and first 5 words to be visible.
US 6 |  | User want to see the recent activity listed with dates.
US 7 |  | User want to delete the note from recent activity.
US 8 |  | User want to access application regardless of browser type.
US 9 |  | User want to know if the storage goes out with recent activity
US 10 |  | User want to be notified with popup for any page reloading in the middle of editing notes.
US 11 | Share notes | User want to share the text with file recorded to any valid mail id.
US 12 |  | User would like to know, If invalid mail id entered.
US 13 |  | User want to access the note while clicking the shared link
US 14 |  | User wants the shared link to be in destination within 15 to 20 seconds

## Iteration Task schedule
Activity | Start Date | End Date
Produce Software | 2021-11-27 | 2021-12-01
Acceptance Test | 2021-12-10 | 2021-12-11
Application release | 2021-12-02 | 2021-12-07
Iteration 2
Activity | Start Date | End Date
Produce Software | 2021-12-30 | 2021-01-02
Migrate iteration 1 Data | 2021-12-30 | 2021-01-20
Acceptance Test | 2021-01-13 | 2021-01-14
Application Release | 2021-01-05 | 2021-01-08

## Iteration Deliverables
Iteration | Deliverable
1 | Installation Scripts User Manual Configuration Data Software Installation Media Release Notes
2 | Same as above adding Data Migration Utility Program

## Test Case
Test Scenario ID | Test scenario | Test Case ID | Test Case Description | Expected Result | Actual Result | Pass/Fail
TS1 | Check the Recent activity functionality | TC1 | Verify user able to view the recent activities by clicking on the tab. | able to view the recent activities successfully
TS2 |  | TC2 | Verify User able to edit the transcribed text. | able to edit the transcribed text successfully.
TS3 |  | TC3 | Verify User able to play back recordings. | able to play back recordings successfully
TS4 |  | TC4 | Verify User able to search the files based on date from recent activity. | able to search the files successfully
TS5 |  | TC5 | Verify User able to search the files based on name from recent activity. | able to search the files successfully
TS6 |  | TC6 | Verify User able to access listing in the recent activity. | able to access listing successfully
TS7 |  | TC7 | Verify User able to delete note from the recent activity. | able to delete note successfully
TS8 |  | TC8 | Verify User able to access the application using any browser. | able to access the application successfully
TS9 |  | TC9 | Verify the user get notified with low memory | user getting notified successfully
TS10 |  | TC10 | Verify User gets popup notification while editing notes for any page reloading. | getting popup notification succesfully
TS11 | Check the share note functionality | TC11 | Verify User able to share text with recorded file to a valid mail address. | able to share text successfully
TS12 |  | TC12 | Verify User is getting error message for invalid mail id enetered | getting error message successfully
TS13 |  | TC13 | Verify User able to access note using the link shared. | able to access note successfully
TS14 |  | TC14 | Verfy user able to recieve shared link within 20 seconds. | Shared link recieved succesfully.

## risk
Risk ID | Risk Description | Effect | Risk Type | Probability | Mitigation Strategy
R1 | Compromisation of Data security may occur | 1. Users will lose the trust in the company 2. Company will be fined by a huge amount. | Business | High | Electronic Key management system can be used for higher security(Stubbs, 2018).
R2 | Implementing technology will be complex with limited knowledge | quality of the system will be reduced | Technical | Medium | Website trusted resource can be reffered.
R3 | Storage may be running out due to the recent note feature | System performance will get affected | Business | Medium | Storage space need be added to the server after regular review.
R4 | Robots.txt file misconfiguration may happen, so that search engines may able to crawl internal page(Inside Out Security, 2013) | Private information will be visible to public in content search | Technical | High | File will be carefully configured based on refering trusted website source and knowledge.
R5 | Unknown viewers may be there for the shared links | Unknown leakage of private data for a long time. | Technical | High | Audit access feature can be a solution with the cloud app providers like google azure cloud
R6 | Complex design and development of database system | Higher expense for the system usage | Business | Medium | Commercial databases can be used and customize them
R7 | Human negligence of the database security measues | Leak of sensitiv data without knowing | Technical | High | Implement security control and policies(Maurer, 2015)
R8 | Exploiting databases that are vulnerabe during operation | Loses sensitive data | Technical | High | Monitoring database real time is one of the solution(The State of Security, 2021)
R9 | Since tamil is not my native language. website design will be difficult. | design may take longer time. | Technical | Medium | Google translator can be used